## Overview
Subgroup | Members
Server | Martynas, Daniel, Cassie
Database | Martynas, Farmina
Mobile App | Jann, Farmina
Web Client | Nadeem, Cassie

## MobileApp
Task | Description | Worked on by | Current Status | Date started | Date Completed | Notes
Set Up - Android Studio | Install Android Studio | Farmina, Jann | Completed
Set Up - Project file | Create basic Hello World app | Farmina, Jann | Completed | 2018-02-20 | 2018-02-23 | FH - I face some constraint issues but finally solved it
Set Up - Github repository | Push a compiling program into github repository | Jann | Completed | 2018-02-23 | 2018-02-23
Screen - Welcome Screen | Welcome screen when you open app | Jann | Completed | 2018-03-04 | 2018-03-04
Design - Registration Screen | Registration screen to gather user input | Farmina, Jann | Completed | 2018-03-07 | 2018-03-05
Screen - Login Screen | Login screen to load corresponding menu | Farmina, Jann | Completed | 2018-03-07 | 2018-03-06
Screen - Registration Type | Screen to determine what kind of registration user wants | Farmina, Jann | Completed | 2018-03-07 | 2018-03-07
Documentation - Workflow | Workflow diagram | Jann | Completed | 2018-03-20 | 2018-03-27
Screen - Client Menu | Client menu options (claim, account, logout) | Jann | Completed | 2018-04-01 | 2018-04-01
Screen - Business Menu | Business menu options (create, account, logout) | Jann | Completed | 2018-04-01 | 2018-04-02
Feature - Navigation bar | Navigation bar | Jann | Completed | 2018-04-01 | 2018-04-03
Screen - Business Registration | Gather Business Info | Farmina, Jann | Completed | 2018-04-01 | 2018-04-08 | FH - Initial design ¦ JI - Adjusted constraints, formatting, naming
Screen - Client Registration | Gather Client Info | Farmina, Jann | Completed | 2018-04-01 | 2018-04-13 | FH - Initial design ¦ JI - Adjusted constraints, formatting, naming
DB - Connect Registration | Pushing registration details to DB | Jann, Martynas | Completed | 2018-04-06 | 2018-05-04 | JI - Will need help with this
DB - Connect Login | Validate login credentials with DB | Martynas | Completed | 2018-04-06 | 2018-05-04 | JI - Will need help with this
Screen - Business Create Package | User input to create package | Jann, Farmina | Completed | 2018-04-18 | 2018-04-22 | FH - Initial design ¦ JI - Adjusted constraints, formatting, naming
Screen - Client Claim Package | User input to enter package ID to claim | Jann | Completed | 2018-04-18 | 2018-04-22
Screen - Client Check Packages | List of claimable packages | Jann | Completed |  | 2018-05-06
Screen - Business Account Information | Basic account information | Jann | Completed | 2018-04-18 | 2018-04-19
Screen - Client Account Information | Basic account information | Jann | Completed | 2018-04-18 | 2018-04-19
DB - Connect Create Package | Push new package info into DB from user input |  | IP
DB - Connect Claim Package | Claim new package and remove from DB |  | IP
DB - Connect Account Information | Pull account info from DB and display to user | Martynas | Completed | 2018-04-17 | 2018-05-04
Feature - Business Menu | Add option to see claimable packages | Jann | Completed | 2018-04-18 | 2018-04-18
Feature - Client Menu | Add option to see claimable packages and to claim packages | Jann | Completed | 2018-04-18 | 2018-04-18
Feature - Session Token | Grant token at login, use token to validate any functions user wants to do | Martynas | Completed |  | 2018-05-04 | JI - Implement this last
Feature - Logout | Disable authorization token and bring user to login page |  | IP |  |  | JI - Implement this last
Function - HTTP POST/REQUEST | Ability to communicate with server using Async function | Jann | Completed | 2018-04-06 | 2018-04-30 | JI - 4/19 still tweaking ¦ JI - 4/30 MC fixed it on server side
Function - Custom Callback | Use a custom callback so we can keep using the same function | Jann, Martynas | Completed | 2018-04-06 | 2018-05-04 | JI - Still needs to implement, do this after getting initial function fixed
Screen - Business Mark Packages | Ability for businesses to mark and delete packages | Jann | Completed |  | 2018-05-04
DB - Connect Mark Packages | Able to set boolean values on DB |  | IP
Screen - Business Claimable Packages | List of claimable packages | Jann | Completed |  | 2018-05-06
DB - Connect Claimable Packages List | List of claimable packages from DB |  | IP

## Server, API
Task | Description | Worked on by | Current Status | Test for Task | Date started | Date Projected | Date Completed | Issues | Notes
Setup Test Server | On local machine for initial development | M, C, D | Completed | Able to connect to local host |  | 2018-02-25 | 2018-02-25
Create ASP.NET Web API project | Become familiarized with ASP.NET Web APIs | M, C, D | Completed | Call local web-server's API to get "hello world" message |  | 2018-02-25 | 2018-02-25
Initial API Implementation | Create route stubs, merge authentication code, commit | D | Completed | It builds and authentication still works |  | 2018-03-25 | 2018-03-28
Initial SMS Gateway Research | Research and decide on SMS Gateway functionality, which service/libraries to use, etc. | M, C, D | Completed |  |  | 2018-03-08 | 2018-03-08 |  | SMS support is dropped; mobile fetch-based notifications only
Configure Authentication | Should register users, store account names and password hashes in database | M, C | Completed | Create test accounts |  | 2018-03-11 | 2018-03-14
Enable API to database functionality | Create the DbContext class. Configure for authentication, user info, client info, package info. | M, D | Completed | Able to add to database from API for all methods that require db info |  | 2018-03-25 | 2018-03-28
Integrate API and Authentication | Update API to handle user requests | M, D | Completed | Test API functions with user info |  | 2018-03-25 | 2018-03-14
Implement basic customer queue | The queue should get local clients and process them, sending client to the end of queue when package is picked up | M, D | WIP | Create a package and check that a regular background job is started to notify the next best unnotified client | 2018-04-07 | 2018-04-22
Ensure API works with web client | Work with the web client team to implement all necessary methods | M, C, D | WIP | Test all paths with range of inputs | 2018-04-08 | 2018-04-22
Ensure API works with mobile client | Work with the mobile team to implement all necessary methods. | M, D | WIP | Test all paths with range of inputs | 2018-04-08 | 2018-04-22
Initial JSON request/response class | Helper functions/library to parse JSON request bodies and create JSON standard acknowledgement strings | C | Completed | Send fake JSON requests and responses that follow the API documentation to the class | 2018-03-21 | 2018-03-25 | 2018-04-04
Finalize authentication response | Add helpful HTTP response headers on authorization failure; handle other FIXMEs | M | Completed | Predictable responses for successful login, successful token-use, unsuccessful login, and unsuccessful token-use |  | 2018-04-15 | 2018-04-20 |  | HTTP status code is enough
Session expiration | Regular background job that deletes expired sessions | M, D | WIP | Let session token expire and ensure it was deleted from database | 2018-04-07 | 2018-04-22
Controller implementations | CRUD API routes for users and packages | M, C, D | Completed | Create, retrieve, claim, receive packages using HTTP requests and responses | 2018-04-01 | 2018-04-07 | 2018-04-07
Input validation | Do input validation wherever MySQL won't catch errors (e.g. non-digits in a phone number) | C | WIP | Send all types of incorrect inputs and check that the system acts accordingly
Controller error handling | If an error occurs, respond with an appropriate HTTP status code and reason phrase | C | WIP | Cause or force errors (in debug mode) and check that the system responds with the right Acknowledgement
Package expiration | Design and implement system's response to packages expiring while in different states |  | Unstarted | Let packages expire when unclaimed, claimed, and received and check that relevant routes and background jobs handle them correctly
Session extension | Implement refresh token system or switch to OpenID Connect which helps us with that |  | Unstarted | Replace a session token with a new one using a refresh token |  | Next Group |  |  | These session-related tasks are not a priority and might be delayed for another semester
Configure CORS | Configure Cross-Origin Resource Sharing in API startup code so requests are only accepted from expected origin domains |  | Unstarted | Front-ends can connect and requests with modified origin cannot

## WebClient
Task | Description | Worked on by | Current Status | Test for Task | Date started | Date Projected | Date Completed | Issues | Notes
Web Page Mockups | Create some mockups to work off of for the front end implementation and to get a better sense of page flow | Nadeem & Cassie | Completed | Verify with rest of team. |  | End of Week 7
Basic Home page | Create homepage with some info about the project | Nadeem | Completed | View exists |  | End of Week 8
Registration Page | Set up frontend for registering clients and businesses | Nadeem | Completed | Can navigate to view |  | End of Week 8
Login | For both clients and businesses | Nadeem | Completed | Can navigate to view |  | End of Week 8
Profile | Able to view profile information | Nadeem |  | Can navigate to view |  | End of Week 8
Edit Profile | Page to edit profile information, update phone number, delete account. | Nadeem |  | Can navigate to view |  | End of Week 8
Initial Front End Implementation | Integrate all of the above views | Nadeem | Completed | Integration Test |  | End of Week 9
CSS Initial | Improve on the design and "feel" of the web client. | Nadeem & Cassie |  |  |  | End of Week 9
Begin to connect to Server | Use API and begin to implement required methods. | Nadeem & Server Subgroup |  |  |  | End of Week 10

## Database
Task | Description | Worked on by | Current Status | Test for Task | Date started | Date Projected | Date Completed | Issues | Notes
Logical Design Initial |  | Martynas, Farmina, Jann | Completed | Create example data + check with workflow diagrams | 2018-02-20 | 2018-02-23 | 2018-02-23
Physical Design Iteration 1 |  | Martynas | Completed | Run MySQL setup script successfully + add example data | 2018-02-23 | 2018-03-04 | 2018-03-04
Physical Design Iteration 2 | Add session_data table and willing_to_pay attribute to client | Martynas | Completed | Creation script runs | 2018-03-21 | 2018-03-21 | 2018-03-21
Update Logical Design Document | Update database diagram to represent latest iteration for documentation purposes | Martynas | Completed | Diagram and creation-script match | 2018-04-06 | 2018-04-15 | 2018-04-06
Add Indexes | Add indexes on certain attributes to make common queries faster | Martynas | Unstarted | Time queries with and without indexes to check for improvement |  | 2018-04-28